## Stakeholders
Name | Role | ELSP | ELSB | Niessen
Ruth Solozábal | M&S Manager | TRUE | TRUE | TRUE
José Manuel Bustamante | OEM Channel Manager | TRUE | TRUE
Antoni Martinez | PBL Channel Manager | TRUE | TRUE
Mario Mora | DIST Channel Manager | TRUE | TRUE | TRUE
Roberto Fernandez | Technical Promotion Manager | TRUE | TRUE
Pau Masgrau | Digital Solutions Sales Manager | TRUE | TRUE
Nora Araico | PMD Smart Buildings |  | TRUE | TRUE
Jarbas Ferro | PMD Jarbas Ferro | TRUE
Pedro Viguera | Marketing Manager
Idoia Matas | Communications Manager |  |  | TRUE
Joan Sola | Pricing and eCommerce Manager
Albert Vives | Data Centers Segment Manager | TRUE | TRUE
Paco Alvarez | Business Development Niessen |  |  | TRUE
Xabier Peña | Regional Sales Manager - North
Abrahan García | Regional Sales Manager - Northeast
Roberto García | Regional Sales Manager - Catalunya | TRUE
Jorge Sanchez Del Rio | Regional Sales Manager - Center
Juan Pedro Puerto | Regional Sales Manager - South
Eduardo Jesus Ager | Regional Sales Manager - Levante
Xavier Quingles | KAM GES
Ghada Kalim | KAM Sonepar
Antonio Lozano | DIY Channel Manager |  |  | TRUE
Josep Borrell | PMS Smart Power | TRUE
Guillermo Gomez | PMS Smart Power | TRUE
Diego Rosa | PMS Smart Power | TRUE
Elsa Cora | PMS Smart Power | TRUE
Roberto Chico | PMS Smart Power | TRUE
Jorge Miguel Lopez | PMS Smart Buildings |  | TRUE
Ane Arin | PMS Smart Buildings |  |  | TRUE
Lluis Vives | PMS Smart Buildings |  | TRUE
Javier Hijona | PMS Smart Buildings |  | TRUE
Marta Blanco | PMS Smart Buildings |  | TRUE
Sonia Galparsoro | PMS Smart Buildings |  |  | TRUE
Juan Antonio Yañes | Business Development Specialist |  | TRUE
Eudald Ferre | Business Development Specialist |  | TRUE
Cleva Medina | Data & Content Specialist |  | TRUE
|  | 14 | 15 | 8

## Sprint 1
OBJECTIVES & KEY RESULTS |  |  | 01/07/2025 - 30/09/2025
What should we focus on and achieve in the next sprint to ensure we deliver the end result as we imagined?
| Create clear and organized work groups | Agree on the mission and how we work together | Identify the main opportunities
| Our goal is to set up the teams and know who is involved. | Our goal is for everyone to understand the plan and their role in it. | Our goal is to understand what the market needs before we create actions.
KEY RESULT 1 | Create 3 "Circles of Interest": one for Smart Power, one for Smart Buildings, and one for Niessen. | Hold meetings ("contracting sessions") with all important stakeholders to agree on what we want to achieve. | Hold "discovery workshops" with all Channel Sales Managers.
KEY RESULT 2 | Make a final list of all the important people (stakeholders) for each of the 3 Circles. | Create a clear, shared "team purpose" document that everyone agrees on. | Create a final document with the top 3-5 strategic opportunities for each sales channel.
KEY RESULT 3 |  |  | Rank these opportunities for each channel using a simple Impact/Effort matrix to guide prioritization.

## Sprint 2
OBJECTIVES & KEY RESULTS |  |  | 01/10/2025 - 31/12/2025
What should we focus on and achieve in the next sprint to ensure we deliver the end result as we imagined?
| Design the first version of the action plans | Add details and get internal agreement | Prepare the tools for success | Present the final plan and get approval
| Our goal is to decide the specific actions with the sales channel teams. | Our goal is to work with the Product Marketing team to make the plans complete. | Our goal is to make sure our Microsoft Lists tool is 100% ready for launch. | Our goal is to successfully present the finished work to management
KEY RESULT 1 | By Oct 10th, finish meetings with all Channel Managers to define the main actions for each of the 3 Circles. | By Oct 31st, finish review meetings with the Product Marketing team to add all details (products, budget, timeline) to the plans. | The Microsoft Lists tool is complete with all final views and custom formats by December 5th. | On December 10th, present the complete 2026 Smarketing plan at the general meeting.
KEY RESULT 2 | By Oct 17th, create the first written version of the action plan for each Circle. | Complete at least one review cycle where Product Marketing provides written feedback and the plan is updated. | Create a simple 1-page user guide or a short "how-to" video on using the tool. | Receive final management approval and implement minor change requests.
KEY RESULT 3 |  | By Nov 14th, get the final written "ok" (sign-off) from both the Channel Managers and Product Marketing leads for all 3 plans. | Hold one training session for all stakeholders to show them how to use the tool and answer questions. | Distribute the final, approved plan document and a link to the MS Lists tool to all stakeholders.

## Sprint 3
OBJECTIVES & KEY RESULTS |  |  | 01/01/2026 - 31/03/2026
What should we focus on and achieve in the next sprint to ensure we deliver the end result as we imagined?
| Successfully launch and manage the plan | Create a strong system for tracking progress | Showcase Early Success to Build Momentum | Gather Feedback to Improve Our Process
| Our goal is to start doing the actions we agreed on. | Our goal is to review our work and learn every month. | Our goal is to highlight quick wins to prove this new way of working is effective. | Our goal is to listen to our stakeholders and make our collaboration even better for the next sprint.
KEY RESULT 1 | Launch 100% of the planned Q1 actions across all 3 Circles by January 31st. | Hold one monthly review meeting for each of the 3 Circles in January, February, and March (a total of 9 meetings). | By February 28th, identify one high-impact "Quick Win" action that has been completed for each of the 3 Circles. | At the end of the sprint, run a short, simple survey (3-4 questions) with all key stakeholders to get their feedback on the process.
KEY RESULT 2 | All action owners update the status of their assigned tasks in MS Lists at least once per month. | Achieve a 90% attendance rate from key stakeholders in all monthly review meetings. | Create a simple, one-slide success story for each of the 3 Quick Wins, showing the action taken and the positive result. | Identify the top 3 suggestions for improvement from the feedback.
KEY RESULT 3 | Achieve at least an 80% on-time completion rate for all actions planned for this sprint. | Identify and document at least one "key learning" or "process improvement" from each of the 3 Circles per month. | Present these success stories to the management team in a brief update to demonstrate early ROI. | Create a concrete action plan to implement at least one of these improvements in Sprint 4 (Q2).